## Stakeholder Specifics
Name | Role | Current state | Interest in initiative | Power in Initiative | Comms style | Personality type | Comms frequency | Current disposition | Needed disposition | Personal fact | Trusted advisors
Tom | ERP Owner |  | Low interest | Low interest | scheduled meeting | Outgoing - Extravert - | Weekly | Major proponent |  | Loves dogs | SAP Consultant
Developers

## Communications
Name of Communication | Format | Frequency | Owner | Distribution | Escalation path | Dashboard
Weekly Status Update | e-mail | weekly | PM | Project team members | LOB owner, CEO
Action Items Follow-up | call and email follow-up | every other day | PMO | Action item owners | Leads, LOB owner
Budget Burndown | face-to-face | Monthly | Business owner, business manager, leads | Leadership | Business manager, CFO
Risks Review and Update | meeting topic | Monthly |  | PM, security, ops, leads | PM, architect, principal engineer, LOB owner
Business impact change | in person | As needed | lead architect | Impacted stakeholders | LOB owner, CEO

## Sheet4 (hidden)
Actively for | email | Low interest
Happy | phone call | High interest
Neutral | text msg | At risk/has stake
Concerned | drive-by | Working against
Actively counter | scheduled meeting
over coffee